## WBS Overview
AI RESEARCH AGENT - WORK BREAKDOWN STRUCTURE (WBS)
SIC Capstone Project - Team 013
PROJECT OVERVIEW
PROJECT: | AI Research Agent - Revolutionary RAG System
DURATION: | 4 Weeks
TEAM SIZE: | 5 Members (Team 013)
METHODOLOGY: | Agile with 1-week sprints
WBS ID | Task Name | Owner | Duration | Deliverables
1 | PROJECT MANAGEMENT
1.1 | Project Planning | Bala Swamy | Week 1 | Project Plan Document
1.2 | Team Coordination | Bala Swamy | Week 1-4 | Meeting minutes, Progress reports
1.3 | Progress Tracking | Bala Swamy | Week 1-4 | Weekly status reports
1.4 | Risk Management | Bala Swamy | Week 1-4 | Risk Management Plan
2 | RESEARCH & DESIGN
2.1 | Technology Research | Sakshi | Week 1
2.1.1 | RAG Systems Study | Sakshi | Week 1 | RAG Research Report
2.1.2 | AI Technologies Review | Sakshi | Week 1 | Technology Feasibility Report
2.1.3 | Database Solutions | Sakshi | Week 1 | Database Selection Document
2.2 | System Architecture Design | Bala Swamy | Week 1-2
2.2.1 | System Architecture | Bala Swamy | Week 1-2 | Architecture Diagram
2.2.2 | Component Design | Bala Swamy | Week 1-2 | Component Specifications
2.2.3 | UI/UX Design | Devesh | Week 1-2 | UI/UX Mockups
3 | DEVELOPMENT - BACKEND
3.1 | Core Infrastructure | Eswar | Week 1-2
3.1.1 | Setup Development Environment | Eswar | Week 1 | Environment Configuration
3.1.2 | Database Implementation | Eswar | Week 1-2 | Vector Database Setup
3.1.3 | API Framework | Bala Swamy | Week 1-2 | RESTful API Structure
3.2 | RAG Engine Development | Eswar | Week 2-3
3.2.1 | Document Processing | Eswar | Week 2 | Document Parser Module
3.2.2 | Embedding Generation | Durga Reddy | Week 2-3 | Embedding Service
3.2.3 | Retrieval System | Eswar | Week 2-3 | Search & Retrieval Module
3.3 | AI Integration | Durga Reddy | Week 3
3.3.1 | LLM Integration | Durga Reddy | Week 3 | LLM API Integration
3.3.2 | Response Generation | Durga Reddy | Week 3 | Response Engine
3.3.3 | Revolutionary Technologies | Durga Reddy | Week 2-3 | 6 Revolutionary Technologies Implementation
4 | DEVELOPMENT - FRONTEND
4.1 | User Interface | Devesh | Week 2-3
4.1.1 | Layout Development | Devesh | Week 2 | Base UI Components
4.1.2 | Query Interface | Devesh | Week 2-3 | Search Interface
4.1.3 | Results Display | Devesh | Week 2-3 | Response UI Components
4.2 | Frontend Integration | Bala Swamy | Week 3
4.2.1 | API Integration | Bala Swamy | Week 3 | Frontend-Backend Connection
4.2.2 | State Management | Devesh | Week 3 | State Management System
5 | TESTING & QUALITY ASSURANCE
5.1 | Unit Testing | Sakshi | Week 2-3
5.1.1 | Backend Unit Tests | Sakshi | Week 2-3 | Backend Test Suite
5.1.2 | Frontend Unit Tests | Sakshi | Week 2-3 | Frontend Test Suite
5.2 | Integration Testing | Sakshi | Week 3
5.2.1 | API Testing | Sakshi | Week 3 | API Test Results
5.2.2 | End-to-End Testing | Sakshi | Week 3 | E2E Test Suite
5.3 | Performance Testing | Sakshi | Week 3-4
5.3.1 | Load Testing | Sakshi | Week 3-4 | Load Test Report
5.3.2 | Accuracy Testing | Sakshi | Week 3-4 | Accuracy Metrics
5.4 | Quality Assurance | Sakshi | Week 3-4 | QA Report
5.5 | Storage Optimization | Eswar | Week 3-4 | Optimized Storage System
6 | DOCUMENTATION
6.1 | Technical Documentation | Devesh | Week 3-4 | Technical Docs
6.2 | User Manual | Devesh | Week 3-4 | User Guide
6.3 | Final Report | All Team | Week 4 | Project Report
7 | PROJECT CLOSURE
7.1 | Final Testing | Sakshi | Week 4 | Final Test Report
7.2 | Project Review | All Team | Week 4 | Lessons Learned Document
7.3 | Final Presentation | Devesh | Week 4 | Presentation Slides & Demo
7.3 | Final Presentation | All Team | Week 4 | Presentation Slides & Demo

## Resource Allocation
RESOURCE ALLOCATION
Team Member | Responsibilities | Allocation %
Bala Swamy (Team Leader) | Project management, Architecture design, API development, Integration, Deployment | 100%
| • Project management | 20%
| • Architecture design | 15%
| • API development | 25%
| • Integration | 20%
Eswar (Data Lead) | Database setup, Document processing, Data pipeline, Storage optimization | 100%
| • Database setup | 30%
| • Document processing | 40%
| • Data pipeline | 20%
| • Storage optimization | 10%
Durga Reddy (Model Builder) | AI model development, Revolutionary technologies, Algorithm optimization | 100%
| • AI model development | 50%
| • 6 revolutionary technologies | 40%
| • Algorithm optimization | 10%
Devesh (Presentation & Demo) | Frontend development, Documentation, Presentation | 100%
| • Frontend development | 40%
| • Documentation | 40%
| • Presentation | 20%
Sakshi (Research & Testing) | Research, Testing, Quality assurance | 100%
| • Research | 20%
| • Testing | 60%
| • Quality assurance | 20%

## Milestones
PROJECT MILESTONES
Week | Milestone | Status
Week 2 | Planning Complete | ✓
Week 4 | Infrastructure Ready | ✓
Week 6 | Document Processing Working | ✓
Week 8 | 3 Technologies Implemented | ✓
Week 10 | All 6 Technologies Complete | ✓
Week 12 | Testing Complete | ✓
Week 14 | Project Completed | ✓

## Budget
PROJECT BUDGET & RESOURCES
Category | Cost | Details
HUMAN RESOURCES
Team Members |  | 5 team members × 4 weeks
TECHNICAL RESOURCES | Free Tier
API Keys (Gemini) | Free Tier | AI model API access
Development Tools | Free Tier | Development and testing tools
SOFTWARE LICENSES | 0 | All open-source (no cost)
TOTAL BUDGET | 0